## Sheet1
Task | Start | Finish | Project
AgroCensus and Crop Yield Detection + Workshop (VU) | 2023-12-01 | 2024-04-30 | DEP
Regional Near-Coastal Satellite Derived Bathymetry using S1/S2 | 2024-02-01 | 2024-06-30 | SDB
Satellite Derived Bathymetry Validation in 4 Countries | 2024-06-01 | 2024-12-30 | SDB
Coastlines Enhancement and Cleanup | 2023-11-01 | 2024-05-30 | DEP
Coastlines Rates of Change and Coastal Erosion | 2024-05-30 | 2024-12-15 | CMSP
Mangroves Enhancement using CoastTrain ML Data with MVI/MFI | 2024-01-01 | 2024-03-30 | MACBLUE
Seagrass Detection (FJ, VU, PNG, SB) | 2024-03-01 | 2024-08-30 | MACBLUE
PacRIS Migration | 2023-11-01 | 2023-12-30 | PCRAFI
LULC and Invasive Species Detection in Identified Areas (FJ, TO) | 2024-05-01 | 2024-07-30 | INV
DEP Production Cloud Infrastructure, Documentation and Cleanup | 2024-01-01 | 2024-02-28 | DEP
Regional GeoMedian S2/LS | 2024-12-01 | 2024-01-30 | DEP
Regional LULC Methodlogy and Classification (S2) | 2024-09-01 | 2024-11-30 | DEP
Marine Habitat Mapping | 2024-07-01 | 2024-12-30 | CMSP
DEP Data Exposure and Dissemination Pipeline | 2024-02-01 | 2024-04-30 | DEP
Finalise dep-tools, Production Creation Pipelines and Workflows | 2024-01-01 | 2024-02-28 | DEP
Nexus Upgrade and Back-end Enhancements | 2023-12-01 | 2024-03-30 | ENVEXP
Nexus Metadata Enhancements | 2023-11-01 | 2024-03-30 | ENVEXP
Add ENVEXP datasets from NIWA and beyond to Nexus | 2024-02-01 | 2024-06-30 | ENVEXP
Develop map viewer for ENVEXP data | 2024-05-01 | 2024-12-30 | ENVEXP
Fiji LandCover Mapping Workshop (Training Data Collect Earth) | 2024-01-22 | 2024-01-26 | DEP
Fiji LandCover Mapping Workshop (DEP) | 2024-02-19 | 2024-02-23 | DEP